## Project Profile
Defect Tracking Sheet
TC_02
Project ID | Group 1
Project Name | Airline Reservation System
Prepared/Modified by | Role | Date of Preparation
Rajat Bhutani
Reviewed by | Role | Date of Review
Ritika Mishra
Approved by | Role | Date of Approval
Tanmaya K Acharya
Circulation List | rajat.aggarwal@capgemini.com rabina.chand@capgemini.com rajat.bhutani @capgemini.com ritika.a.mishra@capgemini.com farah.jamal@capgemini.com priya.b.kaushik@capgemini.com jeeveswar.medavaram@capgemini.com
Version Number | 1

## Defect Tracking Sheet
Project ID: | Group 1 | Project Name : | Airline Reservation System | [22 empty] | VERIFIED
CLOSED
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments |  | REOPENED | Coding |  |  | Internal Dev
D_01 | Modify Employee Information Module | Without Modification the same data is accepted | The Data should be modified when the user clicks on modify option but even though it is not modified it can be accepted and saved. | Coding | Chrome | Eclipse | P2 | Low | 1 | 1 | 19/07/2018 | Lakshmi Priya. N | Yamini.N | ACTIVE | PPR | NA | Yamini.N | 20/07/2018 | 20/07/2018 | Tejasri.M | 1 | 1 | NA | Not Fixed | SR | CNR | New Requirement | P2 | High | External QA
D_02 | Login credentials Information Module | Giving Incorrect Username is not producing error message | After giving wrong username as input it is not displaying the error message. Instead it is waiting until the password is entered and then displaying the error message accordingly. | Coding | Chrome | Eclipse | P2 | Low | 1 | 1 | 19/07/2018 | Lakshmi Priya.N | Lakshmi Kalyani.M | ACTIVE | PPR | NA | Lakshmi Kalyani.M | 20/07/2018 | 20/07/2018 | Tejasri.M | 1 | 1 | NA | Not Fixed | RT | REP | Documentation | Low
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: prioritise the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.

## Revision History
REVISION HISTORY OF WORK PRODUCT (to be maintained by projects)
# | Date | Version # | Section Changed | Details of changes made | Approved By